## UFDR Risk
Risk # | Risk | Type | Likelihood | Impact | Mitigation | What Happened | What We Did | Results
R-01 | Developer Hire | Human Resource | H | H | If it looks like we won't have a developer for a long time, be sure to favor technologies where there is in-house expertise already developed. | Didn't have developerfor 1st quarter of project. 2nd quarter had a developer that wasn't the right fit. Could not hire a semantic developer with appropriate level of expertise. | Re-architected the application so we could hire PHP developer for front-end developer. Project Manager to take over implementation of semantics. | Project Manager allocated 90-95% on semantic implementation (training, back-end querying, logic and testing) and only 5-10% of time on Project Management.
R-02 | Fixed Time-Frame contraint on project. Development timelines not controlled by developer. | Schedule | H | H | Short time-frame is seen as advantage to get stakeholders interested and involved. Can alter one of the triangle: money, scope, resources. First, try to limit scope. Prioritize functionality. Second, ask for more money to extend timeline. Third, supplement resources (from CDL) | Due to issue in finding developer with semantic expertise, the development timeline was significantly shortened from 1 year to 6 months. | We prioiritized functionality and what was seen as truly optional (as stated in initial grant and confirmed by stakeholders) was jettisoned. 1. We didn't limit scope. 2. We ended up with money for extension of project for an additional month. 3. We ad hoc supplemented with CDL resources for development gaps. (beg, borrow, steal) | We met nearly all base requirements. When resources were allocated more deliberately, we worked as team to implement with open communication and process.
R-03 | UFDR - Not getting community support. | Community | M | H | 1. Dependent on outcome of stakeholder meeting. 2. Mitigate through transparency of project management (e.g. use wiki to show schedule). 3. Mitigate through early prototype and release to stakeholders to increase their confidence in the project. (this introduces another risk: Agile) | We planned a successful stakeholder meeting (in the middle of a threated federal shut-down) to get feedback and some involvement from key stakeholders. | Developed open-development on wiki w/ documentation and bug-tracking. Monthly community updates and mailing list. Released a beta for users to test and give feedback in October. Some project management documentation (e.g. scheulde) was difficult to keep up due to time allocation of only 5-10% on total PM tasks from Project Manager. | A partnership with some key stakeholders. Others are MIA.
R-04 | Agile - Frequent prototype and community response cycles | Process | M | H | Don't have a lot of experience with Agile cycles. Mitigate by "getting better" at the administration of releases and incorporation of community feedback. | We incorporated feedback from stakeholders on key questions during various points in development cycle. We also incorporated feedback from beta release. | Tried various tools from sprint spreadsheets to combined wiki/bug tracking to manage Agile cycle. Due to necessary iterative testing and the nature of the application, the sprint spreadsheets were difficult to manage because nothing ever really "fell off the list". Switching to primary bug tracking with versions and components was more successful, but was only used by the PM. | Because the typical process of bug-tracking wasn't followed, this resulted in extra work from the PM. Breaking up the tasks into releases and components was the most successful way to manage this development. However, there were some features lacking in tool (such as excel export) which made tracking difficult. Weekly status meetings helped as we split the time between status and technical issues. PM and developer worked together daily. Proximity of cube placement and compatibility made it easy to do joint development.
R-05 | Equipment - No plan to buy additional equipment. Plan to fit into existing architecture (dev + prod environments). Believe we have sufficient capacity | Hardware/ Software | L | L | Most likely this is not a risk. After review of our current computing resources, it is possible to add a dev/prod environment. Will there be a need for a staging site? If the end result is a web site for the stakeholders to view, then the dev site can be the 'staging site'. | This was not seen as a risk. However, ended up being a high risk late in the project.
R-06 | Storage Creep - Currently need 1. Triple/quad store, 2. Test files, 3. Index, …? The test files may be large and we may need to separate out the storage for performance | Hardware/ Software | L | M | Not necessary to implement the storage of test files (Or specifications and other documentation) in this phase, but the design should take into consideration this future need.
R-07 | Synchronization - How well is this technology understood? | Human Resource | M | L | Not necessary to implement in this phase. However, must have a design that doesn't preclude this implementation in the future. Perhaps it is as simple as offering a tag in the data model for Private/Public. The granularity would be a the Class-level for Format and its associated triple assertions.
R-08 | Decision - Public versus Private Data | Community | M | L | Find out from stakeholders as early as possible, the preference for the ability to maintain some registry data on independent instances and what type of support is needed for "promotion" or "publication" to the Public versions. This may necessitate the need for a more complex versioning support which would take some time in designing scenarios. It is already known that people will want to store private data in local instances of registries. The nove above for Synchronization applies to this risk (private/public tag).
R-09 | Decision - Eligibility - Who is allowed to contribute to the registy (anyone? Or a registered list) This could affect access control… | Community | M | H | As a straw man to be discussed at stakeholder meeting (pulled from UDFR calls/emails): Accept contributions from anyone, but allow users to register their identities (and institutional affiliations) with the system. All format information should be tagged with contributor identity information (if only to indicate anonymous contribution). Information consumers could be allowed to "rate" the information, similar to the way in which many social networking sites rely on user reputation to establish veracity. The interface and API should allow registry users to view data contributor and affiliated inst. and opt to only see/get data from those they trust or highly rated/reviewed data.
R-10 | Decision - What level of review is needed on contributed data to take place? This affects the data model and potentially architecture. Need to decide level of granularity and potential ideas for governance. | Community | M | H | You need a strategy for this one! Consider time scoping the decision-making. Identify a representative steering committee of stakeholders with Y/N power.
R-11 | Non-availability of getting PRONOM seed data | Community | L | H
R-12 | Not finding appropriate open-source tools (e.g. semantic wiki) that meet functional requirements | Hardware/ Software | L | M
R-13 | Data model is too complex for implementing fully. We may not have the software or developer expertise to implement the model fully | Human Resource | M | H | Mitigate by creating a subset/kernal. Start with the PRONOM Core UNIONED with GDFR (or is there also a GDFR "core"?). Semantic web technologies help mitigate as it's easy to add on to the model later on.
R-14 | Large Project Size (Duration) Over 6 months is considered High Impact | Schedule | H | H | Mitigate by smaller phases and phased implementation. See Agile.
R-15 | Project Decision-Making Unclear. As the Stakeholder group is from a diverse group of organizations, we need to develop a clear decision-making model. The current idea is that we try for consensus at the Stakeholder Meeting. "Sponsoring/Decision making committee" is defined as Medium Impact. | Community | H | M | Mitigate by 1. specifying decision-makers' role within project documentation (and wiki). 2. Add tasks to the Project Plan for involving decision-makers and managing relationship with them. 3. Identify key decision-makers before the Stakeholder Meeting and work directly with them on consensus. (see (2))
R-16 | Environmental State. Yet to be Deployed is identified as High Impact. | Hardware/ Software | H | H | Mitigate by 1. compare notes with other deployments (e.g. Merritt) which may have some similar requirements. 2. Allow time for additional testing. 3. Develop prototype in new environment. We were thinking of having Dev/Prod set up at same time. Not sure the value of having the Prod site set up at the same time as dev. If the architecture changes as a result of testing, it means the Prod site will need to be changed which is more work than chaning dev.
R-17 | Technology Change and Support. We are depending on open-source tools which may have limited support , testing, debugging. | Hardware/ Software | H | H | A) don't pick tools only 1 person knows. B) don't use 1.0 versions C) if open source, choose tools with actual communities, etc.